## Week 2
Daily Stand-up Meeting Report
Week: Jun 12 - Jun 16
Project Name: Automated Grading and Feedback Tools for Java
Team Name: Street Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Siva Reddy Mekapothula | Made some analysis on grading rubric | Analyzed the rubric grading
| Discussed with the team members and gathered suggestions on grading rubric and started again working on it | Desiging the rubric grading
| No issues yet | No issues yet
Harish Babu Achanta | Made some analysis on the requirements gathered from client and its possibilites | Some analysis on on client interface requirement
| Discussed with the team members and gathered suggestions on UI requirements related to student point of view and started working on the suggestions | Had a discussion whether they affect the application or not.
| No issues yet | No issues yet
Vamshi Krishna Girikala | Made some discussion like whether requirement is useful or not on the Admin(i.e.instructor) requirements. | Discuss on interface of Admin view
| Discussed with the team members and gathered their suggestions and worked on suggestions. | Analyzing the interface of Admin view
| No issues yet | No issues yet
Madanamohan Reddy Govindu | Had a Discussion with the team and gathered some information regarding UI requirements from Admin poin tof view | Working on the team suggestion of grading system
| Working on the requirements based on the information collected from the team | Working on the team suggestion of grading system
| No issues yet | No issues yet
Venkatesh Katragadda | Made some conclusion on grading process requirements | Working on the team suggestion of rubric design
| Discussed with the team and made some changes in the requirements and gathered more information from discussion and started analyzing on it | Working on the team suggestion of rubric design
| No issues yet | No issues yet
Sunil Kumar Sangaraju | Analyzed on the drawaback in the existing system and made a note of it | Analyzing the drawabacks of grading tool
| Discussed on the drawbacks with the team and started analyzing how far these drawbacks affecting the grading process | Finding the best grading tool
| No issues yet | No issues yet
Prasanthi Rani Bhogaraju | Research on grading system | Analyzing the grading system
| Research on grading system | Analyzing the grading system
| No issues yet | No issues yet
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 1
Daily Stand-up Meeting Report
Week: Jun 12 - Jun 16
Project Name: Automated Grading and Feedback Tools for Java
Team Name: Street Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Siva Reddy Mekapothula | 1) Got strengths and weakness of the team | 1) Assignes roles to the team | 1) Read requirements gathering document. | 1) Analyzing the requirements | 1) Read github
| 2) Reading through the project | 2) Read some research papers | 2) Analyzing the requirements | 2) Read Github | 2) Research on grading rubric
| 3) Don't have clear understanding of the project yet | 3) Understanding the project | 3) No Issues yet | 3) No obstacles yet | 3) No obstacles yet
Harish Babu Achanta | 1) Understanding the client expextations and project. | 1) Research on platforms which is suitable for our project | 1) Got the clear idea of the project. | 1) Working on UI requirements | 1) Working on UI requirements from student point of view
| 2) Reading through the project | 2) Understanding the client expextations and project. | 2) worked on UI requirements from student point of view | 2) Gathered some requirements from client regarding UI from student point of view | 2) Analyzing on the requirements gathered from client and its possibilites
| 3) Don't have clear understanding of the project yet | 3) Understanding the project | 3) Should get to know all the possible cases from the Client requirements | 3) No issues yet | 3) No issues yet
Vamshi Krishna Girikala | 1) Discussing on requirements | 1) Reading through the project | 1) Reading through the project | 1) Reading through Admin (i.e.instructor) requirements. | 1) Reading through Admin (i.e.instructor) requirements.
| 2)Reading through the project | 2) Should get a clear view about requirements. | 2) Got some idea about project | 2) Reading through Admin (i.e.instructor) requirements. | 2) Analyzing the Admin(i.e.instructor) requirements.
| 3) Don't have clear understanding of the project yet | 3) Understanding the project | 3) No Issues yet | 3) Need some information about Admin (i.e.instructor) Functions | 3) No issues yet
Madanamohan Reddy Govindu | 1) Reading reasearch papers | 1) Make a requirements document. | 1) Study about the project and its importance | 1) Working on the UI requirements from Admin point of view | 1) Working on UI requirements from admin point of view
| 2) Yet to decide roles | 2) Documenting all inputs | 2) Trying to get more information about the project. | 2) Gathered some requirements from client regarding UI from Admin point of view | 2) Analyzing on the requirements gathered from client and its possibilites
| 3) Don't have clear understanding of the project yet | 3) Understanding the project | 3) No Issues yet | 3) Need more information regarding UI requirements | 3) Need more information regarding UI requirements
Venkatesh Katragadda | 1) Finding the existing applications in the real world. | 1) Reading through the existing applications | 1) Had some reasearch on existing applictions. | 1) Done the research on Existing application | 1) Reading through the grading process requirements
| 2) Yet to decide roles | 2) Got to know about my role | 2) Got some idea about project | 2) Had a client meeting | 2) Reading through the grading process requirements
| 3) Don't have clear understanding of the project yet | 3) Understanding the project | 3) No Issues Yet | 3) No issues yet | 3) No issues yet
Sunil Kumar Sangaraju | 1) Reading through the existing application | 1) Research some tools which are used to the project. | 1) Got some idea about project | 1) Had a client meeting | 1) Analyzing the existing tools
| 2) Yetto decide roles | 2) Got to know about my role | 2) Studying the implementations of tools | 2) Analyzing the existing tools | 2) Finding drawbacks of existing tools if any
| 3) Don't have clear understanding of the project yet | 3) Understanding the project | 3) No Issues yet | 3) No issues yet | 3) No issues yet
Prasanthi Rani Bhogaraju | 1) Read Some articles regarding project | 1) Had some research on existing application. | 1) Knowing the client credential requirement | 1) Analyzing the different types of credentials | 1) Some research on scanninng the source code
| 2) Reading through the exisiting project | 2) Got to know about my role | 2) Gathering requirements on credentials | 2) Had a client meeting | 2) Research on grading system
| 3) Don't have clear understanding of the project yet | 3) Understanding the project | 3) No Issues yet | 3) No issues yet | 3) No issues yet
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?