## Instructions
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Mentor, and Project Description fields
For each issue identified, complete the following:
A | ID: A unique ID number used to identify the issue in the issue tracking log.
B | Current Status: This column should be populated with the issue's current status. o Open: The issue is currently open but has not yet been addressed. o Work In Progress: The issue is being actively worked to develop a resolution. o Closed: The issue is no longer considered an active project threat and can be closed with or without resolution. Some other potential options include: o Late: The issue resolution is not yet resolved and it is past the expected resolution date. o On Hold: The issue has been put on hold. o Combined: Two issues found to be similar have been combined.
C | Priority: This column should be populated with the priority of the issue. Valid options include the following: High, Medium, Low. These are defined as follows: o Critical: Issue will stop project progress if not resolved. o High: Issue will likely move the project back in terms of budget or timeline, or will materially affect quality or scope. o Medium: Issue will have material effect on project, has potential to be moved to high category and/or requires significant resources to manage. o Low: Issue is expected to have a moderate effect on the project, but will require resources to address.
D | Issue Description: This column should be populated with a description of the issue.
E | Assigned to Owner: This column should be populated by the name of the issues owner. The individual most responsible for working towards resolving the issue.
F | Expected Resolution Date: This column should be populated with the date that the issue is expected to be resolved.
G | Escalation Required (Y/N): This column should be populated with “Yes” if the program/project manager feels an issue needs to be escalated and “No” if escalation is not needed to resolve the issue.
H | Impact Summary: This column should be populated with a description of the impact of the issue. The impact may be expressed in terms of one or more of the following: schedule, scope, resources, and space. The impact description should also include a reference to any milestones impacted.
I | Action Steps: This column should be populated with the proposed steps to address the issue. Examples include, but are not limited to, developing alternatives analysis or submitting a change request.
J | Issue Type: This column should be populated with the issue type. Valid options include the following: FRI, Procedural, System, Other. These are defined as follows: o Informational: The issue was generated and logged in response to a request for information external to the immediate project/project team. o Procedural: The issue impacts process or procedure. o System: The issue impacts systems (hardware or software). o Other: The issue impacts other areas.
K | Date Identified: This column should be populated with the date that the issue was identified.
L | Associated ID(s): This column should contain the project ID of any associated milestones that may be impacted by an issue or that the issue is dependant upon for resolution. Please note, this value may require coordination with other program/project managers or the PMA.
M | Entered By: This column should be populated by the name of the individual who first identified the issue.
N | Actual Resolution Date: This column should be populated with the date that the issue was actually resolved.
O | Final Resolution & Rationale: This column should be populated with a description of the final resolution & rationale of the issue. The resolution may be expressed in terms of one or more of the following: schedule, scope, resources, and space. The resolution description should also include a reference to the milestones impacted.
Column | Instructions For Changing the Contents of Drop-Down Menus
B, C G, J | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field

## Issues Tracking
ISSUE MANAGEMENT LOG | [7 empty] | ISSUE MANAGEMENT LOG
Project Name: |  |  | Automated Grading and Feedback Tool For Java |  |  |  |  | Project Name: | Automated Grading and Feedback Tool For Java
Project Mentor: |  |  | Dr. Michael Oudshoorn |  |  |  |  | Project Mentor | Dr. Michael Oudshoorn
Project Description: | [7 empty] | Project Description:
ID | Current Status | Priority | Issue Description | Assigned To Owner | Expected Resolution Date | Escalation Required (Y/N)? | Impact Summary | Action Steps | Issue Type | Date Identified | Working Hours | Entered By | Actual Resolution Date | Final Resolution & Rationale
1 | Closed | High | Communication Gap: The entire team is not on the same boat, some of them used different mediums to communicate. | Sivareddy Mekapothula | 2017-06-10 | No | Possability of project work not completed on time | Meet the team members and clarify what medium they all commonly use for communication and collabration | Informational | 2017-06-08 | 7 Hours | Sivareddy Mekapothula | 2017-06-11 | The project team met with all its members to clarify the individual problems allowing the project to move forward as planned.
2 | Closed | Critical | Unaware of clear-cut goals resulting in scope change | Sivareddy Mekapothula | 2017-06-17 | Yes | Potential project stoppage | Make appointments with the client to have a proper requirements | Procedural | 2017-06-14 | 15 Hours | Harish Achanta | 2017-06-17 | Appointments are made to ensure the goals of the project are met
3 | Closed | High | Scope creep: Scope may change during the development process. | Sivareddy Mekapothula | 2017-06-18 | Yes | Possability of project work not completed on time | Make a solid acceptance plan and walk the client through it for his approval | Procedural | 2017-06-16 | 8 Hours | Venkatesh | 2017-06-18 | Do not deviate from the acceptance plan and work accordingly
4 | Closed | Critical | User Credentials: We have certain dubts about password minimum length , password contains which letters(characters, numbers, special characters) | Sivareddy Mekapothula | 2017-06-24 | Yes | Possability of project work not completed with in time | Make appointments with the client to have a proper requirements | Functional | 2017-06-20 | 12 Hours | Vamshi | 2017-06-25 | After certain client meetings we got clear requirements about user credentials
5 | Closed | Low | Punctuality: Sometimes team members are not punctual to the time meetings due to various valid reasons | Sivareddy Mekapothula | 2017-06-21 | No | No such big impact as other issues | Talk to the team members and clarify their actions | Other | 2017-06-21 | 2 Hours | Sunil Kumar | 2017-06-21 | Discussed with the team members and made them to agree on being punctual to the meetings
6 | Closed | Critical | Heuristics rules:Have an issue with grading rules | Sivareddy Mekapothula | 2017-07-03 | Yes | May effect the entire functionality of the system | After Certain client meeting we got up with the solution | Functional | 2017-06-29 | 18 Hours | Sivareddy Mekapothula | 2017-07-05 | Discussed with the client and team members, became with the solution.
7 | Closed | Critical | Feedback Design : We have an issues with which information should keep in feedback pattern | Sivareddy Mekapothula | 2017-07-07 | Yes | May effect the entire functionality of the system | After Certain client meeting we got up with the solution | Functional | 2017-06-30 | 20 Hours | Madan Mohan | 2017-07-07 | Discussed with the client and team members, became with the solution.
8 | Closed | Medium | Unavailablity of Team members: Some times team members might not be available for certain reasons | Sivareddy Mekapothula | 2017-07-11 | No | possability of project work not completed on time | Have proper project manangement plan and allocate team resources accordingly | Procedural | 2017-07-10 | 4 Hours | Prashanthi | 2017-07-11 | Plan and allocate work accordingly, have backup plans if a team member is not available.
Note on A5: • ID: A unique ID number used to identify the issue in the issue tracking log.
Note on B5: • Current Status: This column should be populated with the issue's current status. o Open: The issue is currently open but has not yet been addressed. o Work In Progress: The issue is being actively worked to develop a resolution. o Closed: The issue is no longer considered an active project threat and can be closed with or without resolution. Some other potential options include: o Late: The issue resolution is not yet resolved and it is past the expected resolution date. o On Hold: The issue has been put on hold. o Combined: Two issues found to be similar have been combined.
Note on C5: • Priority: This column should be populated with the priority of the issue. Valid options include the following: High, Medium, Low. These are defined as follows: o Critical: Issue will stop project progress if not resolved. o High: Issue will likely move the project back in terms of budget or timeline, or will materially affect quality or scope. o Medium: Issue will have material effect on project, has potential to be moved to high category and/or requires significant resources to manage. o Low: Issue is expected to have a moderate effect on the project, but will require resources to address.
Note on D5: • Issue Description: This column should be populated with a description of the issue.
Note on E5: • Assigned To Owner: This column should be populated by the name of the issues owner. The individual most responsible for working towards resolving the issue.
Note on F5: • Expected Resolution Date: This column should be populated with the date that the issue is expected to be resolved.
Note on G5: • Escalation Required (Y/N): This column should be populated with “Yes” if the program/project manager feels an issue needs to be escalated and “No” if escalation is not needed to resolve the issue.
Note on H5: • Impact Summary: This column should be populated with a description of the impact of the issue. The impact may be expressed in terms of one or more of the following: schedule, scope, resources, and space. The impact description should also include a reference to any milestones impacted.
Note on I5: • Action Steps: This column should be populated with the proposed steps to address the issue. Examples include, but are not limited to, developing alternatives analysis or submitting a change request.
Note on J5: • Issue Type: This column should be populated with the issue type. Valid options include the following: FRI, Procedural, System, Other. These are defined as follows: o Informational: The issue was generated and logged in response to a request for information external to the immediate project/project team. o Procedural: The issue impacts process or procedure. o System: The issue impacts systems (hardware or software). o Other: The issue impacts other areas.
Note on K5: • Date Identified: This column should be populated with the date that the issue was identified.
Note on L5: • Associated Milestone ID(s): This column should contain the project ID of any associated milestones that may be impacted by an issue or that the issue is dependant upon for resolution. Please note, this value may require coordination with other program/project managers or the PMA.
Note on M5: • Entered By: This column should be populated by the name of the individual who first identified the issue.
Note on N5: • Actual Resolution Date: This column should be populated with the date that the issue was actually resolved.
Note on O5: • Final Resolution & Rationale: This column should be populated with a description of the final resolution & rationale of the issue. The resolution may be expressed in terms of one or more of the following: schedule, scope, resources, and space. The resolution description should also include a reference to the milestones impacted.