## Week 5
Daily Stand-up Meeting Report
Week: July 10 - July 14
Project Name: Automated Grading and Feedback Tools for Java
Team Name: Street Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Siva Reddy Mekapothula | Working on tools which are used for scanning the java source code | Analyzing the identified tools used for scanning | Working on Updating the Data management paln Document | Updated the Data management plan document | Working on updating the issue management plan document
| Identifying the tools which are used for scanning | Documenting the pros and cons of each identified tool | Had a discussion with the team members and noted the suggestions | Had a discussion with the team members and noted regarding the Issue tracking | Updated the Issue management plan Document
| No issues yet | No issues yet | No issues yet | Noted some issues regarding data management plan | No issues yet
Harish Babu Achanta | Working on data management and processing | Working on identified pros and cons of using server | Working on updating the Requirements Document | Updated the Requirements Document | Working on updating the prototypes of the application
| Identifying either to have a server or database for data processing | Had a Discussion with the team noted the suggestions from the other memebers | Had a discussion with the team regarding the updating the modifying the requirements. | Had a discussion with the team members about the modified requirements and discussed about the updating the prototypes | Updated the prototype document
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Vamshi Krishna Girikala | Working on improving the uses cases of the application | Working on documenting the modified use cases | Working on documenting the weekly group meetings | Working on updating the weekly documents of the group meetings | working on the final presentation talk to be delivered to client
| Had discussion with the client and made some modifications | Had a discussion with the client regarding the up coming accomplishments | Updating the past weekly group meetings clearly stating the purpose of the meeting | Had a discussion with the team members and updated the document | Had a discussion with the team members regarding the presentation talk
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Madanamohan Reddy Govindu | Working on the software Architecture | Analyzing the specifications of the software architecture | Working on the software architecture | Working on updating the software architecture | Updated the software architecture
| Identifying the specifications for software architecture | Had a discussion with the team noted down the suggestion regarding the specifications of the software architecture | Had a discussion with the team members and client regarding the improvement of the software architecture. | Had a discussion with the team members on modifying the software architecture. | Discussed with the team members on the updated software architecture
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Venkatesh Katragadda | Working on improving the prototypes of the application related to student | Considering the suggestions from the client and analyzing the possibility started improving the prototypes | Working on updating the minutes of meeting document | Working on updating the time and effort estimation document | Working on documenting some notes in user manual
| Had a meeting with the client and discused about the improvements of the prototypes | Working on documenting the improvements of the prototypes | Working on modifying the client meeting discussions document | Working on modifying the time and effort estimation document | Working on documenting some notes in Installation gudie
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Sunil Kumar Sangaraju | Working on documenting the test plan of the application | working on documenting the test suite of the application | Working on documenting the testplans | Working on updating the testplans document | Working on documenting the test suits document
| Had a Discussion with the team members and made some changes based on their suggestion | Had a Discussion with the instructor about the test suite plan and made some changes in doing that | Had a Discussion with the team members regarding the test plans of the application | Had a Discussion with the team members regarding testplans | Updated the test suits document
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Prasanthi Rani Bhogaraju | Working on modifying and improving the Gantt chart | Working on documenting the modified Gantt Chart | Working on updating the use cases document | Working on updating the use case documents | working on documenting the functional specification
| Had a Discussion with the team and instructor and made some improvements | Had a discussion with the instructor regarding future accomplishments | Had a discussion with the team members and updated the use case document | Had a discussion with the team members regarding updating the use cases | Updating the functional specifications document.
| Need to include the milestones | No issues yet | No issues yet | No issues yet | No issues yet
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 4
Daily Stand-up Meeting Report
Week: July 03 - July 07
Project Name: Automated Grading and Feedback Tools for Java
Team Name: Street Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Siva Reddy Mekapothula | Work on the functional specifiactions along with vamshi | Had a Discuusion with the team memebrs regarding the functional specififcations | Working on updating the group meeting documents based on the suggestions of the instructor | Working on Group weekly meeting documents based on the suggestions of the instructor | Working on updating the group weekly meeting documents .
| Working Documenting the gathered requirements | Noted the suggestions and started working on that and upadting them | Had a Discussion with the team member about the suggestions from the instructor | Noted the suggestions and started working on that and updating them | Working on updating the document
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Harish Babu Achanta | Working on the data managament plan | Had a Discussion with the team about how important the database is for our application | working on updating the requirements related to Instructor functionalitites | Working on updating the requirements related to student functionalities | Working on requirements documentation
| work on analyzing the use of database for the application | Noted the suggestions from the team and started analyzing . | Had a Discussion with the client and team members regarding the additional functionalities. | Had a Discussion with the client and team members regarding the additional functionalities | Working on updating the requiremnts document
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Vamshi Krishna Girikala | Working on functional specifications along with siva reddy | Working on the updating the functional specifications | Working on updating the work break down structure | Working on updating the work break down structure | Working on the gathering the functional specifications
| Had a discussion with the team about the functional specifications | updated the document with functional requirements | Had a Discussion with the team and noted the suggestions | Had a discussion with the team and updated the document | Had a Discussion with the team and started analyzing the specifications
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Madanamohan Reddy Govindu | Working on the software architecture | Working on updating the software architecture | Working on the Instructor use cases based on instructor suggestions | Working on updating the login use case | Working on updating the use case related to instructor
| Had a discussion with the team about the application and gathered more information about it. | Had a discussion on updated software architecture with the team. | Had a discussion on the suggestions made by instructor with the team | Updated the document containing use cases | Working on updating the document containing use cases
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Venkatesh Katragadda | Worked on updating the project management plan after discussion with the team member responsbile for WBS | Worked on the project management plan document of work break down structure | working on the updating the project management plan document | Working on analyzing the time estimate for the project based on the project management plan | Working on the time estimate for the project based on project management plan
| Had a discussion with the team and explained the updated components of the project management plan | Had a discussion with the team member working on Gantt chart | Had a Discussion with the team about the cost managmenet plan | Had a Discussion with the team members regarding the amount of time tobe spent on the project according to project management plan | Working on documenting the time estimate
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Sunil Kumar Sangaraju | Working on improving the prototypes of the student view | Updated the prototype of the Student view | Working on the updating the student view prototype particullarly uploading the assignment view | Working on updating the student view prototype particullarly on viewing the feedback of grading | Working on documenting the prototypes of the student view
| Analayzing the problems of student view on the existing system . | Analayzing the problems of the instructor view in the existing system | Analyzing the problems of the existing system and discussing with the team | Had a discussion with the team regarding the improvement of the prototype | Working on the documenting the student view protypes
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Prasanthi Rani Bhogaraju | Working on development of Gantt chart | Working on the improvement of Gantt chart | Working on the updating the student use case | Working on updating the student use case based on the functionalities | Working on documenting the use cases
| Had discussion with the team meber working on WBS | Updated the Gantt chart by adding the milestones | Had a discussion with the team and instructor | Had a discussion with the team members and instructor | Working on updating the document containing usecases
| Need to include the milestones | No issues yet | No issues yet | No issues yet | No issues yet
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 3
Daily Stand-up Meeting Report
Week: Jun 26 - Jun 30
Project Name: Automated Grading and Feedback Tools for Java
Team Name: Street Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Siva Reddy Mekapothula | Working on login requirements for student and instructor | Working on login requirements for student and instructor | Worked on the meeting minutes document that should be submitted to client | Working on the types of login required for the student | Worked on the type sof the login required for the student considering the suggestions from the team
| Working on login requirements for student and instructor | Identifying the issues till now | Worked on the documentation | Had a Discussion with the team members and gathered the suggestions regarding the types of login required for the student | Documented the type of the login needed and worked on its pros and cons
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Harish Babu Achanta | Gathering Functional requirements | Gathered functional requirements | Worked on the documenting the client requirements | Worked on the basic mock up of the student view of the application | Updated the Mock up of the student view
| Gathering Functional requirements | Works on Mock ups | Modified some requirements based on the team and client suggestions | Had a Discussion with the team and improved the mock up of the student view | Had Discussion with the team about the pros and cons of the Mock up created
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Vamshi Krishna Girikala | Working on use cases for test case evaluation, error reporting and feedback module | Worked on use cases for test case evaluation, error reporting and feedback module | Worked on the work break down structure for project management plan Document | Worked on updating the use cases of the Student functionalities | Worked on the upadting the student functionalities in the system
| Working on use cases for test case evaluation, error reporting and feedback module | Designing usecases for test case evaluation, error reporting and feedback module | Worked on the Gantt chart | Had a discussion with the team and modified some the functionalitites | Updated the use cases of the student .
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Madanamohan Reddy Govindu | Working on use cases for compilation and Execution module | Worked on use cases for compilation and Execution module | Working on the Software architecture | Working on updating the use cases of the instructor functionalities | Worked on adding the functionalitites to the istructor on application
| Working on use cases for compilation and Execution module | designing usecases for compilation and Execution module | Had discussion with the client and Team about the Software architecture | Had a discussion with the team and added more functionalitites to the instructor | Worked and updated the use cases of the instructor
| No issues yet | No issues yet | Need more inforamtion about the application | No issues yet | No issues yet
Venkatesh Katragadda | Gathering Functional requirements | Gathered functional requirements | Worked on the project management plan document that should be submitted to client | Worked on updating the project management plan document | Worked on mock up of the instructor view of the application
| Gathering Functional requirements | Works on Mock ups | Had discussion with the team members who are responsbile in preparing WBS | Had a Discussion with the team and gathered some suggestions to be impleted in the WBS | Had a discussion with the team and updated the mock up of instructor view of the application
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Sunil Kumar Sangaraju | Working on login requirements for student and instructor | Worked on login requirements for student and instructor | Worked on creating the test plan | Worked on gathering the different types of the test cases | Worked on upadting the different types of the test cases needed for the application
| Working on login requirements for student and instructor | Identifying the issues till now | Had a discussion with the team memebers regarding the test cases of the requirements | Had a discussion with the team on the gathered test cases and statrted to updated the test cases | Worked on updating the test pla document
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Prasanthi Rani Bhogaraju | Working on use cases for login, file upload modules and visualizing the statistics module | Worked on use cases for login, file upload modules and visualizing the statistics module | Worked on the usecases documentation | Working on updating the all use cases of the system and documenting it | Worked on the updating the use cases document
| Working on use cases for login, file upload modules and visualizing the statistics module | designing usecases for login, file upload modules and visualizing the statistics module | Had discussion with the team on the use cases | Had a discussion with the team memebers working on the use cases and started updating the use case document | Had a discussion with the team and explained and discussed the updated use case dcoeument
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 2
Daily Stand-up Meeting Report
Week: Jun 19 - Jun 23
Project Name: Automated Grading and Feedback Tools for Java
Team Name: Street Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Siva Reddy Mekapothula | Made some analysis on grading rubric | Analyzed the rubric grading | Desiging the rubric grading | Designed rubric grading | collected test cases for login module
| Discussed with the team members and gathered suggestions on grading rubric and started again working on it | Desiging the rubric grading | Desiging the rubric grading | working on test cases | working on test plan document
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Harish Babu Achanta | Made some analysis on the requirements gathered from client and its possibilites | Some analysis on client interface requirement | working on requirement document | worked on requirements document | worked on prototypes
| Discussed with the team members and gathered suggestions on UI requirements related to student point of view and started working on the suggestions | Had a discussion whether they affect the application or not. | working on requirement document | Discussed with the team members for prototypes | works on requirement document
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Vamshi Krishna Girikala | Made some discussion like whether requirement is useful or not on the Admin(i.e.instructor) requirements. | Discuss on interface of Admin view | Desiging the Admin view | Desigined the Admin view | Design use cases to admin view
| Discussed with the team members and gathered their suggestions and worked on suggestions. | Analyzing the interface of Admin view | Desiging the Admin view | Design use cases to admin view | Working on use cases document
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Madanamohan Reddy Govindu | Had a Discussion with the team and gathered some information regarding UI requirements from Admin poin tof view | Working on the team suggestion of grading system | Gathered grading system requirements | working on software architecture | worked on software architecture
| Working on the requirements based on the information collected from the team | Working on the team suggestion of grading system | Discuss software architecture of the project | working on software architecture | Working on use cases for compilation and Execution module
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Venkatesh Katragadda | Made some conclusion on grading process requirements | Working on the team suggestion of rubric design | Gathered grading system requirements | working on student view UI interface | Design student view UI interface
| Discussed with the team and made some changes in the requirements and gathered more information from discussion and started analyzing on it | Working on the team suggestion of rubric design | working on student view UI interface | Designing student UI view interface | working on project management plan
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Sunil Kumar Sangaraju | Analyzed on the drawaback in the existing system and made a note of it | Analyzing the drawabacks of grading tool | Finds grading tools | Gathered some test cases | gathered test cases
| Discussed on the drawbacks with the team and started analyzing how far these drawbacks affecting the grading process | Finding the best grading tool | Discuss test cases | Gathering test cases | working on test plan document
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Prasanthi Rani Bhogaraju | Research on grading system | Analyzing the grading system | Discuss with the client and team members about grading system | Modified grading requirements according to the suggestions given by client and team members | Documenting the client meetings, weekly meetings and standup meetings
| Research on grading system | Analyzing the grading system | Modifing grading requirements according to the suggestions given by client and team members | Documenting the client meetings, weekly meetings and standup meetings | Working on use cases for login, file upload modules and visualizing the statistics module
| No issues yet | No issues yet | No issues yet | No issues yet | No issues yet
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 1
Daily Stand-up Meeting Report
Week: Jun 12 - Jun 16
Project Name: Automated Grading and Feedback Tools for Java
Team Name: Street Coders
| Monday | Tuesday | Wednesday | Thursday | Friday
Siva Reddy Mekapothula | 1) Got strengths and weakness of the team | 1) Assignes roles to the team | 1) Read requirements gathering document. | 1) Analyzing the requirements | 1) Read github
| 2) Reading through the project | 2) Read some research papers | 2) Analyzing the requirements | 2) Read Github | 2) Research on grading rubric
| 3) Don't have clear understanding of the project yet | 3) Understanding the project | 3) No Issues yet | 3) No obstacles yet | 3) No obstacles yet
Harish Babu Achanta | 1) Understanding the client expextations and project. | 1) Research on platforms which is suitable for our project | 1) Got the clear idea of the project. | 1) Working on UI requirements | 1) Working on UI requirements from student point of view
| 2) Reading through the project | 2) Understanding the client expextations and project. | 2) worked on UI requirements from student point of view | 2) Gathered some requirements from client regarding UI from student point of view | 2) Analyzing on the requirements gathered from client and its possibilites
| 3) Don't have clear understanding of the project yet | 3) Understanding the project | 3) Should get to know all the possible cases from the Client requirements | 3) No issues yet | 3) No issues yet
Vamshi Krishna Girikala | 1) Discussing on requirements | 1) Reading through the project | 1) Reading through the project | 1) Reading through Admin (i.e.instructor) requirements. | 1) Reading through Admin (i.e.instructor) requirements.
| 2)Reading through the project | 2) Should get a clear view about requirements. | 2) Got some idea about project | 2) Reading through Admin (i.e.instructor) requirements. | 2) Analyzing the Admin(i.e.instructor) requirements.
| 3) Don't have clear understanding of the project yet | 3) Understanding the project | 3) No Issues yet | 3) Need some information about Admin (i.e.instructor) Functions | 3) No issues yet
Madanamohan Reddy Govindu | 1) Reading reasearch papers | 1) Make a requirements document. | 1) Study about the project and its importance | 1) Working on the UI requirements from Admin point of view | 1) Working on UI requirements from admin point of view
| 2) Yet to decide roles | 2) Documenting all inputs | 2) Trying to get more information about the project. | 2) Gathered some requirements from client regarding UI from Admin point of view | 2) Analyzing on the requirements gathered from client and its possibilites
| 3) Don't have clear understanding of the project yet | 3) Understanding the project | 3) No Issues yet | 3) Need more information regarding UI requirements | 3) Need more information regarding UI requirements
Venkatesh Katragadda | 1) Finding the existing applications in the real world. | 1) Reading through the existing applications | 1) Had some reasearch on existing applictions. | 1) Done the research on Existing application | 1) Reading through the grading process requirements
| 2) Yet to decide roles | 2) Got to know about my role | 2) Got some idea about project | 2) Had a client meeting | 2) Reading through the grading process requirements
| 3) Don't have clear understanding of the project yet | 3) Understanding the project | 3) No Issues Yet | 3) No issues yet | 3) No issues yet
Sunil Kumar Sangaraju | 1) Reading through the existing application | 1) Research some tools which are used to the project. | 1) Got some idea about project | 1) Had a client meeting | 1) Analyzing the existing tools
| 2) Yetto decide roles | 2) Got to know about my role | 2) Studying the implementations of tools | 2) Analyzing the existing tools | 2) Finding drawbacks of existing tools if any
| 3) Don't have clear understanding of the project yet | 3) Understanding the project | 3) No Issues yet | 3) No issues yet | 3) No issues yet
Prasanthi Rani Bhogaraju | 1) Read Some articles regarding project | 1) Had some research on existing application. | 1) Knowing the client credential requirement | 1) Analyzing the different types of credentials | 1) Some research on scanninng the source code
| 2) Reading through the exisiting project | 2) Got to know about my role | 2) Gathering requirements on credentials | 2) Had a client meeting | 2) Research on grading system
| 3) Don't have clear understanding of the project yet | 3) Understanding the project | 3) No Issues yet | 3) No issues yet | 3) No issues yet
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?